## Roadmap
Roadmap
Milestone/Task | # Issues | Time | Dependencies | Update | Time | Defintion
Build Platform |  |  |  |  | Short-term | Activity for the next 3 months
Milestone 2 - MVP |  |  |  |  | Medium-term | Activity for the next 6 months
Create Landing page | #15 | Short-term | Line 62 - Dependant on User flow for MVP | SR and AR have begun development on this | Long-term | Activity for the next 12 months
Create Sign up/Sign in flow | #17 | Short-term | Line 62 - Dependant on User flow for MVP
Create View Experiences page | #105 | Short-term | Line 62 - Dependant on User flow for MVP
Create My Stories MVP page | #19 | Short-term | Line 62 - Dependant on User flow for MVP
Create Share Experience MVP | #16 | Short-term | Line 62 - Dependant on User flow for MVP
Milestone 3 - Open Humans Integration
Retrieve experiences from database | #106 | Short-term
Integrate sign-in process using Open Humans with interface | #102 | Short-term
Allow user to save an experience and view experiences not yet submitted | #101 | Short-term
Moderator sign-in | #100 | Short-term
Store text input in Open Humans back end with appropriate tags | #99 | Short-term
Document Open Humans link | #98 | Short-term
Place-holder moderation page | #20 | Short-term
Milestone 4 - Accessibility Checks
HTML checks - Check any video players are accessible | #68 | Medium-term
HTML checks - check the language the content is written in | #67 | Medium-term
HTML checks - Checking tables and bullet lists are styled properly | #66 | Medium-term
Search and other forms of navigation | #65 | Medium-term
Check whether there’s an alternative for people who cannot see maps | #64 | Medium-term
Pop-ups and interactive or flashing content | #63 | Medium-term
Checking content is usable when zoomed in or magnified | #61 | Medium-term
Navigating just using a keyboard | #60 | Medium-term
Tests using a mobile or tablet device | #59 | Medium-term
Check the PDFs and other documents | #58 | Medium-term
Check users can review their answers before submitting a form | #56 | Medium-term
Check that any error messages are helpful | #55 | Medium-term
Check users get a warning before they’re timed out | #54 | Medium-term
Check form elements are consistent across your website | #53 | Medium-term
Check it’s clear what information users need to provide | #52 | Medium-term
Check form fields are marked up appropriately | #51 | Medium-term
Check you’re using proper headings | #42 | Medium-term
Check pages are usable when stylesheets are disabled | #43 | Medium-term
Check for images containing text | #50 | Medium-term
Audio descriptions for video and audio content | #49 | Medium-term
Check any video or audio content is properly described | #48 | Medium-term
Check any images have a description | #47 | Medium-term
Check that pages have good titles | #46 | Medium-term
Check that form elements behave as expected | #57 | Medium-term
Check that links make sense | #45 | Medium-term
Check that instructions are styled properly | #44 | Medium-term
Milestone 5 - deploy MVP platform | here | Medium-term
Milestone 6 - platform second phase | here | Long-term
Integrate modertaion into platform | #97 | Long-term
Diversity, Accessibility and Inclusivity
Define Accessibility requirements | #496 | Short-term
Check PDFs and other documents for accessibility | #409 | Short-term
Glossary of terms | #73 | Short-term
MVP - User testing to ensure accessibility |  | Medium-term | Accessibility requirements need to be defined first
MVP - Testing against WCAG and gov guidelines |  | Medium-term
Look into opportunities for visual expression on the platform | #376 | Medium-term | Dependency on the platform development and what is possible
User testing to ensure accessibility |  | Long-term | Accessibility requirements need to be defined first
Testing against WCAG and gov guidelines |  | Long-term
Platform Design
User flow mapped out for MVP | #107 |  |  | Completed
Platform branding | #429
Userflow mapped out for second phase platform
Future Funding
List out funding applications | #464 | Short-term
Map out deadlines for funding |  | Medium-term
Apply to funding |  | Long-term
Growing community
Map out onboarding process | #420 | Short-term
Create onboarding pack | #420 | Short-term |  | On PPT
Update Turing Website | #465 | Short-term
Personas and pathway evaluation | #467 | Short-term
Tidy repositories to ensure up to date information and correct links | #415 | Short-term
Provide feedback on the Github repository | #363 | Short-term
Create a communication plan | Here | Short-term
Produce participation strategy | Here
Set up fortnightly reporting | #452 | Short-term
Monthly newsletter |  | Short-term
Find more opportunities for dissemination and community engagement | #417
Code of Conduct for meet-ups updating | #432 | Short-term
Build connections across Turing | #418 | Medium-term
Connect with people who can make changes based on data | #470 | Medium-term
Publish paper(s) on project
Find literature for paper | #481 | Short-term
Drafting papers for Publishing |  | Long-term
Chapter writing |  | Long-term
Opportunities for disseminetion of project outputs and research | #417 | Long-term
Design moderation process
Map out tasks which need decision and dependencies | #476 | Short-term
Create moderation summaries | #416 | Short-term | Lots of the following work is dependant on this
Going through summaries and picking out themes to inform work |  | Short-term
Code of conduct for stories | #475 | Short-term | Other work will be dependant on this
Map out escalation route for undecided stories | #479 | Medium-term
Write guidelines for moderators | #473 | Medium-term
Decide how many moderators are needed | #474 | Medium-term
Assign Moderators | #474 | Long-term
Project management
Expand the project to look at co-occuring conditions | #464 | Short-term
Update documents to include co-occuring conditions | #464 | Short-term
Complete updates on Researchfish | #459 | Short-term
Review and carry out Ethical process | #463 | Short-term
Update Guide to issues | #428
Create a guide to subgroups | #427
Collect dataset using platform which is useful for research
Define what data will be used |  | Long-term
Decide where this will be shared |  | Long-term
Decide how to communicate the data |  | Long-term