## Slide 1: Fortnightly Progress Updates
AutSPACEs

## Slide 2
Nº Issues Raised | 
Nº Issues Closed | 
Nº Pull Requests Raised | 
Nº Pull Requests Merged | 
Progress update | Fortnight: BLANK TEMPLATE
Community Updates:
Platform Development Updates:
Research Updates:
Tasks completed this fortnight: | Upcoming tasks for next fortnight
Blockers:

## Slide 3
Nº Issues Raised | 14
Nº Issues Closed | 4
Nº Pull Requests Raised | 4
Nº Pull Requests Merged | 2
Progress update | Fortnight: 10/05/21 - 24/05/21
Community Updates: Newsletters went out (17/05/21) Meet-up on Thursday Roadmap being developed Co-working on Moderation
Platform Development Updates: Learning Django Creating a landing page Looking at issues and how they fit into the roadmap CSS Bootstrap for landing page
Research Updates: Annual Health update sent to the Turing Researchfish update for Autistica 54 pages of moderation summaries Ethics renewal process for project has started
Tasks completed this fortnight: | Upcoming tasks for next fortnight
Began Roadmapping (#462) | Roadmap Completion (#462)
Researchfish Draft (#459) | Ethics Renewal
May Newsletter (#443) | Funding (#464)
Health Update (#460) | Platform Development issues organisation
Blockers:
Moderation – need to complete summaries before other work can continue

## Slide 4
Nº Issues Raised | 9
Nº Issues Closed | 1
Nº Pull Requests Raised | 6
Nº Pull Requests Merged | 1
Progress update | Fortnight: 25/05/21-07/06/21
Community Updates: Roadmap developed and to be made inclusive by creating it in different formats (word and markdown) Set up co-working for Platform Development Onboarding new members
Platform Development Updates: User flow mapped out Created html pages according to figma wireframes Updating readme files in GitHub Creating mind maps to provide granular details for issues
Research Updates: Moderation summaries Ethics renewal application Invite to partake in panel discussion at Autistica Festival – congratulations to Citizen Scientists SF and JS for getting involved and progressing the work on moderation
Tasks completed this fortnight: | Upcoming tasks for next fortnight
Roadmapping almost complete (#462) | Guidelines from summaries (472)
Repo Refresh begun (415) | Review of Researchfish (#459)
User flow mapped out (107) | Moderation summaries for review (416)
 | Looking into Open Humans integration for sign up flow (102)
 | Complete Roadmapping (#462)
 | Continue Repo Refresh (415)
 | Continue development for Milestone 2
Blockers:

## Slide 5
Nº Issues Raised | 7
Nº Issues Closed | 1
Nº Pull Requests Raised | 16
Nº Pull Requests Merged | 5
Progress update | Fortnight: 10/06/21 – 24/06/21
Community Updates: Newsletter Continued co-working space for platform development Facilitating moderation work Assigning issue to contributors that ensures successful collaboration and work
Platform Development Updates: Continued development on MVP Looking at how the pages link together Regular Co-working sessions
Research Updates: Continued work on Ethics renewal Work on moderation aspect of the platform
Tasks completed this fortnight: | Upcoming tasks for next fortnight
MVP pages completed: Moderation My Experiences (#105) Landing Page (#15) | To complete MVP pages: My Stories (#19) Sign in/up flow (#17) Share experiences (#16)
Moderation guidelines (#472) | Link pages together to reflect User Flow
Continued Ethics progress and draft (#505) | Complete Milestone 2
Draft Newsletter (#498) | Send out moderation summaries and guidelines (#472)
Roadmapping (#462) | Renew the documentation for Ethics (#505)
 | Get views on moderation decisions from wider community (#476)
Blockers: